## Original Backlog
Product Backlog
Priority | Backlog Item | Estimate (person-hours)
1 | As [student] I want to be able to submit a form with parameters as a proposal. | 20
1 | As [administrator] I want an outputted file for a scheduling period. | 10
2 | As [administrator] I want to be able to check proposals in the queue through a visual interface. | 30
2 | As [administrator] I want to be able to modify the queue through "drag-and-drop" functionality | 20
3 | As [student] I want to be able to login to the system, so that I can schedule time for an observation. | 10
3 | As [student] I want to be able to logout of the application in order to ensure account safety and ensure successful termination of my session. | 5
3 | As [administrator] I want to be able to login to the system to view the schedule and make appropriate changes. | 5
3 | As [administrator] I want to be able to logout of the application to ensure account safety and successful termination of my session. | 5
4 | As [administrator] I want to have all functionality that a student has, so that I can have proposal-submission functionality. | 10
4 | As [administrator] I want to see times in the queue that are already reserved so I know what times are still available. | 5
4 | As [adminstrator] I want to be able to edit submitted forms/proposals and choose to accept or deny them. | 10
4 | As [student] I want to see times in the queue that are already reserved so I know what times are still available. | 10
4 | As [student] I want to be able to cancel a proposal if I need a different observation time. | 3
5 | As [administrator] I want to be able to create accounts, so that I can manage student users. | 10
5 | As [administrator] I want to be able to delete accounts, so that I can manage student users. | 3
5 | As [administrator] I want to be able to modify accounts, so that I can manage student users. | 5
5 | As [administrator] I want to be able to override schedule conflicts (if a student holds a time slot I want), so that I can make last minute changes. | 10
6 | As [administrator] I want to be able to manually edit (change text in) the XML files if necessary. | 5
7 | As [student] I want to be notified when my observations have been captured. | 10
7 | As [student] I want to receive my observations through an email/scheduling application. | 15
8 | As [administrator] I want to have access to a user manual that explains how to perform various administrative tasks. | 10
8 | As [student] I want to have access to a tutorial that shows how to submit, edit, or cancel proposals. | 15
| Total: | 226

## Sprint 1 Backlog
Sprint 1 - Sprint Backlog
Task ID | Priority | Backlog Item | Estimate (person-hours)
Form Submission | 1 | As [student] I want to be able to submit a form with parameters as a proposal. | 10
File Output | 1 | As [administrator] I want an outputted file for a scheduling period. | 20
Added
|  | [N/A] | 0
|  | TOTAL: | 30

## Product Backlog
Current Product Backlog As of: Sprint 2 (After Sprint 1)
Priority | Backlog Item | Estimate (person-hours)
2 | As [administrator] I want to be able to check proposals in the queue through a visual interface. | 30
2 | As [administrator] I want to be able to modify the queue through "drag-and-drop" functionality | 20
3 | As [student] I want to be able to login to the system, so that I can schedule time for an observation. | 10
3 | As [student] I want to be able to logout of the application in order to ensure account safety and ensure successful termination of my session. | 5
3 | As [administrator] I want to be able to login to the system to view the schedule and make appropriate changes. | 5
3 | As [administrator] I want to be able to logout of the application to ensure account safety and successful termination of my session. | 5
4 | As [administrator] I want to have all functionality that a student has, so that I can have proposal-submission functionality. | 10
4 | As [administrator] I want to see times in the queue that are already reserved so I know what times are still available. | 5
4 | As [adminstrator] I want to be able to edit submitted forms/proposals and choose to accept or deny them. | 10
4 | As [student] I want to see times in the queue that are already reserved so I know what times are still available. | 10
4 | As [student] I want to be able to cancel a proposal if I need a different observation time. | 3
5 | As [administrator] I want to be able to create accounts, so that I can manage student users. | 10
5 | As [administrator] I want to be able to delete accounts, so that I can manage student users. | 3
5 | As [administrator] I want to be able to modify accounts, so that I can manage student users. | 5
5 | As [administrator] I want to be able to override schedule conflicts (if a student holds a time slot I want), so that I can make last minute changes. | 10
6 | As [administrator] I want to be able to manually edit (change text in) the XML files if necessary. | 5
7 | As [student] I want to be notified when my observations have been captured. | 10
7 | As [student] I want to receive my observations through an email/scheduling application. | 15
8 | As [administrator] I want to have access to a user manual that explains how to perform various administrative tasks. | 10
8 | As [student] I want to have access to a tutorial that shows how to submit, edit, or cancel proposals. | 15
| Total: | 196

## Sprint 2 Backlog
Sprint 2 - Sprint Backlog (Set to Start Sprint 2 on January 12, 2015)
Task ID | Priority | Backlog Item | Estimate (person-hours)
| 2 | As [administrator] I want to be able to check proposals in the queue through a visual interface. | 30
| 2 | As [administrator] I want to be able to modify the queue through "drag-and-drop" functionality. | 20
Added
|  | [N/A] | 0
|  | TOTAL: | 50