## Current Burndown Chart
Time (person-hours (p-h))
Sprint | Average Expectation | Ideal Remaining | Planned Remaining | Actual Effort | Added Reuirements | Estimated Remaining
0 |  | 226 | 226 | 0 | 0 | 226
1 | 38 | 188 | 196 | 29 | 0 | 197
2 | 38 | 150 | 147
3 | 38 | 112
4 | 38 | 74
5 | 38 | 36
6 | 36 | 0